## Gantt planification
Untitled project
Sanggil Han
2019-04-02 00:43
|  | March 2019 |  |  |  |  | April 2019 | [21 empty] | May 2019
 | time axis 2019-03-25 to 2019-06-14
Project activities | Status | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
[Class]Practice Sinnaps | doing ok | bar: 2019-04-01 to 2019-04-02
Finish Sequence Diagram | doing ok
Make "Sinnaps" and put together | doing ok | bar: 2019-04-02 to 2019-04-05
Complete "Modeling Practices" | todo
[Holiday]Easter | todo | bar: 2019-04-15 to 2019-04-22
[Class]Practice JUnit &amp; MOCKITO | todo
Complete "JUnit" | todo | bar: 2019-04-29 to 2019-05-06
Labor Day | todo
Activity 1 | todo | bar: 2019-05-07 to 2019-05-10
[Class]Practice MOCKING | todo
Review Exam | todo | bar: 2019-05-08
Exam | todo
Build PetsApp | todo
Develop PetsApp | todo | bar: 2019-03-26 to 2019-04-01; 2019-04-03 to 2019-05-15; 2019-06-03 to 2019-06-14
Debug PetsApp | todo
[Class]Practice TDD | todo
Finalize PetsApp | todo
Present "PetsApp" | todo

## Project overview
Untitled project
Sanggil Han
2019-04-02 00:43
Project team | Role
Sanggil Han (sanggil) | Project owner
Activity | Involved | Goals | Subtasks | Assigned to | Date | Time
[Class]Practice Sinnaps
1 Apr 2019 - 2 Apr 2019 (2 days) |  | No goals | No subtasks
Finish Sequence Diagram
1 Apr 2019 - 2 Apr 2019 (2 days) |  | No goals | No subtasks
Make "Sinnaps" and put together
2 Apr 2019 - 5 Apr 2019 (4 days) |  | No goals | No subtasks
Complete "Modeling Practices"
8 Apr 2019 - 12 Apr 2019 (5 days) |  | No goals | No subtasks
[Holiday]Easter
15 Apr 2019 - 22 Apr 2019 (6 days) |  | No goals | No subtasks
[Class]Practice JUnit &amp; MOCKITO
23 Apr 2019 - 30 Apr 2019 (6 days) |  | No goals | No subtasks
Complete "JUnit"
29 Apr 2019 - 6 May 2019 (6 days) |  | No goals | No subtasks
Labor Day
1 May 2019 - 1 May 2019 (1 days) |  | No goals | No subtasks
Activity 1
7 May 2019 - 10 May 2019 (4 days) |  | No goals | No subtasks
[Class]Practice MOCKING
7 May 2019 - 8 May 2019 (2 days) |  | No goals | No subtasks
Review Exam
8 May 2019 - 8 May 2019 (1 days) |  | No goals | No subtasks
Exam
13 May 2019 - 13 May 2019 (1 days) |  | No goals | No subtasks
Build PetsApp
14 May 2019 - 17 May 2019 (4 days) |  | No goals | No subtasks
Develop PetsApp
16 May 2019 - 31 May 2019 (12 days) |  | No goals | No subtasks
Debug PetsApp
16 May 2019 - 28 May 2019 (9 days) |  | No goals | No subtasks
[Class]Practice TDD
21 May 2019 - 22 May 2019 (2 days) |  | No goals | No subtasks
Finalize PetsApp
30 May 2019 - 3 Jun 2019 (3 days) |  | No goals | No subtasks
Present "PetsApp"
4 Jun 2019 - 4 Jun 2019 (1 days) |  | No goals | No subtasks